Elaboration of a proposal for the environmental monitoring of sediments along the shoreline of the entire Baltic Sea, concentrating on the harbours and their vicinity, using ostracods from grabs and cores – as part of the HELCOM MONAS Programme. - Establishing an ad hoc working group for intersessional work

PROJECT DESCRIPTION

- Title of Project

Paleoenvironmental study of sediments in harbours of the Baltic Sea using ostracods

Sediment cores for ostracod monitoring project (SCOMP)

2. Project Manager

Dr. D. Keyser

Biozentrum Grindel

Zoologischen Institut und Museum

Martin-Luther-King Platz 3

D-20146 Hamburg

Germany

Tel. + 49.(0)40-42838-4232

Fax + 49.(0)40-42838-3937

Keyser@zoologie.uni-hamburg.de

3. Proposing Party     Germany

Contracting Party          __ Terms of Reference for the Corresponding Group on the Evaluation of a HELCOM :

SCOMP -Sediment Cores for Ostracod Monitoring Programme-

The correspondence group is established by HELCOM MONAS in order to:

- Elaborate a proposal for a HELCOM SCOMP harbour and shoreline sedimentation monitoring programme including:

- identification of stations representative for defined harbour regions in the national boundaries of all riperian states of the entire Baltic Sea

- the access to the places by small vessels from the shoreline

- the financiell effort of collecting and processing sediment samples taken with grabs, dredges and handhold corers

- quality assurance procedures and comparable sampling procedures

- sampling frequencies along the whole shoreline of the entire Baltic Sea

- securing the expertise needed through workshops and project meetings

2.	taken into account:

- experiences from the contracting parties

- experiences gained from the sediment baseline study

3. 	report on the progress of the intersessional work to the MONAS meetings

___
Commission                    _____
Subsidiary body             _____
Heads of Delegation      _____
Executive Secretary      _____

4. The body supervising the project

HELCOM MONAS

5. Target and activities

Targets:

To set up a baseline of healthy environmental condition

To inform about the present state of the sediment environment inferred from ostracod (and diatom) communities

To elaborate the biodiversity of ostracods in the entire Baltic Sea

To specify some indicator species

Activities:

Port and harbours are hot spots of anthropogenic development and environmental changes

The history of changes is preserved in the sediments,

Ostracods are well suited for revealing information in sediment.

- They are present in small sediment samples for they have a small size <1 mm.

- They possess a calcified shell which is readily fossilized.

- The shell is very distinct for each species and can be recognised easily

- Their biodiversity and abundance in the Baltic Sea is high

- They occur in nearly all known water bodies from deep sea into freshwater

- Their environmental boundaries and preferences are known, so that they can be 
assigned to certain environmental factors and thus give information of the 
bio-system at a certain historic or geological time

The comprehensive work should study the vicinity of about 70 harbours around the entire Baltic Sea coast. It should be a supranational project involving scientists from every riparian country of the Baltic Sea. Many of the scientists in the different countries have already been consulted and the response is great, so that we will get a sound basis for such a study.

Sampling will be collected during day trips using small boots as shipping time is limited and expensive, in so doing, more trips can be made and optimal sediment sites chosen. In some harbour this might be difficult. To overcome this we back the harbour samples up with undisturbed sediment cores from the vicinity as reference cores.

The cores should be taken with a hand corer, where we expect short cores with a length of about 50 cm in general. They are divided in 1 cm sub-samples which are analysed for ostracods and possibly for diatoms.

Prior to the start of the programme an atlas of the known ostracods of the Baltic Sea is compiled and will be distributed to all scientists involved.

6. Expected results

The palaeo-sedimentary investigations on ostracods will give information on:

Study of recent ostracod communities to determine the actual state of the environment

Changes from the historical (geological) environmental situation to the recent one

Changes in biosystems over time

Information on the impact of oil in former times

Climatic change manifested by the biogeographically distribution of ostracods

Acidity of water and sediment by the obvious decalcification of the valves

The documentation of the biodiversity of ostracods in the entire Baltic Sea

Influence of the introduction of foreign species into the Baltic Sea

Nomination of indicator species

7. Consistency with HELCOM priorities

yes ____ no

If YES, please give reference e.g. MONAS 8/2005, HABITAT Dokument 7.1

8. Timetable (including number of Project Team meetings)

| 2006 | 2007 | 2008 | 2009 |  |
| --- | --- | --- | --- | --- |
| Asking for approval by HELCOM | Nomination of Partners | 2.Workshop to evaluate and harmonize sampling and analyse activities | 3. Workshop Discussion of results Publication of results Follow up suggestions |  |
| Funding negotiations | Kick off meeting | Report of preliminary results | Preparing database for the Web |  |
| Preparation of a Baltic Sea Ostracod Atlas for general use | 1. Workshop on standardisation methodology |  | Electronical and other publications |  |
|  | Distribution of sampling gear |  | Recommendations |  |
|  | First series of sampling | Second series of sampling and analysing |  |  |
|  | Ostracod analyses |  |  |  |
|  | Database installation |  |  |  |
|  | Sample dating | Sample dating |  |  |

9. Budget (taking into account financial year from 1 July to 30 June)

9.1 Total Costs

Labour cost

Sample preparation and analyses

| Amount of Habours | Amount of cores | Amount of samples(ca.30/core) | Duration of preparation and analysing of sample | Necessary time for prepare and analyse samples | Price /hour | Necessary amount for preparation and analysing samples |
| --- | --- | --- | --- | --- | --- | --- |
| 70 | 350 | 10500 | 3 hours | 31500 hours | 5,00€ | 157 500.00 € |

Travel and subsistence

Estimation of sampling and travel days

|  | distance | Sampling days | Travelling days | days | Allowance/day | Meetings (3x) | Flights (3x) | subsistence |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ca. 30000 km | 70 | ca. 130 | 200 | 110 € | 33 Persons x12 days | 30 Personsx 400€ | 22000 € |
| Gasoline | ca. 6000 € |  |  |  |  | 43560 | 12000 | 6000 € |
|  |  |  |  |  |  |  |  | 75 560 € |

# Equipment

|  | Corer | GPS | Rope | Salinity measurement | Temperatur | pH Meter | Camera | Sieves | Boatal rent |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number | 11 | 11 | 1000 m | 11 | 11 | 11 | 11 | 33 | 70 days |  |
| Price | 11 000 | 5500 | 1500 | 1500 | 1000 | 2500 | 3300 | 3300 | 10 000 | 39 600 € |

# Consumables

| Frankecells | Bottles | Fixation fluid | Postal services |  |
| --- | --- | --- | --- | --- |
| 20000 | 11000 | 11ltr Ethanol |  |  |
| 10000 | 8000 | 2000 | 3000 | 23 000 € |

Other costs

| C14 dating (400€) | 210 PB dating(150 €) |  |  |  |
| --- | --- | --- | --- | --- |
| 140 | 140 |  |  |  |
| 56000 | 21000 |  |  | 77 000 € |

Sum							372 660 €

+ 20 % Overhead   				  74 400 €

Total (estimation) for three years			446 400 €

9.2 Costs divided per financial year

|  | 2007 | 2008 | 2009 |
| --- | --- | --- | --- |
|  | 130 000 € | 200 000 € | 116 400 € |

9.3 Sources of financing divided per financial year

Not known at this time

10. Additional requests (manpower, equipment, facilities, etc.)

10.1 From the Contracting Parties

Access to transportation to the sampling places e.g. car

Laboratory facilities to prepare and sort the samples, including Ekman grab and dredge.

Microscope to analyse the samples

10.2 From the Secretariat

Help in connecting this project with other running projects covering part of the same research objective e.g. the LIFE project.

11. Procedure of nomination of the Project team members

Already contacted with a positive answer following Scientists:

Prof.Dr. N. Aladin Laboratory of Brackish Water Hydrobiology, Zoological Institute of RAS, Universitetskaya nab. 1, 199034, St.Petersburg, Russian Federation (Ecology)

Dr. P.Frenzel, Institute of Geosciences, University of Jena, Burgweg 11, D - 07749 Jena, Germany (Paleontology)

Prof. Dr.B.Scharf, Emmericher Str. 27, D-46286  Dorsten-Rhade, Germany (Paleolimnology)

Prof. Dr. Andrzej Witkowski, Szczecin, Dept. of. Palaeoceanography, Institute of Marine Sciences, University of Szczecin, Waska 13, PL-71-415 Szczecin, Poland (Palaeoozeanography, diatomist)

Prof. Dr. Ragnar Stockholms universitet, SE-106 91 Stockholm Sweden (Marine ecology)

Lithuania - Sergej Olenin

Estonia - Henn Ojaveer

Kaliningrad: Elena Naumenko, Elena Kareseva and Elena Ezhova.

12. Signature of the Project Manager

13. Opinion of the Chairmen of the relevant body

14. Opinion of the Executive Secretary

15. Decision of the Heads of Delegation
(Reference is to be given to the relevant Minutes of the Heads of Delegation's Meeting)

_____ to establish ____not to establish